|  |  |  |
| --- | --- | --- |
|  |  THE REPUBLIC OF UGANDA  | **KAYUNGA DISTRICT LOCAL GOVERNMENT****Office of the Senior Community Development Officer****P.O.Box 18000****KAYUNGA**  |
|  |
| In any correspondence on this subject please quote **Date: 20th March, 2018** E-MAIL**:** **caokayunga@hotmail.com**,**caokayunga@yahoo.com**, **caokayunga@gmail.com** |

The Chief Administrative Officer,

Kayunga District

Thru: The District Community Development Officer,

Kayunga District

**UWEP IMPLEMENTATION STATUS REPORT**

Kayunga district is one of the districts that are implementing UWEP program an interest free financial credit to women groups .The program started in FY 2016/2017 with 25 groups being funded reaching out to 402 women in the district.

In the second phase the district submitted 45 women groups and only 7 women groups have been funded and recoveries have not started.

So far the district has so far received 110,958,000/= since inception and so far the district has recovered 20,603,000 and the balance is 90,355,000/= totaling to 27 % of recovery.

In phase 1 some women groups have responded with repayment with Nazigo and Kitimbwa performing well.

***Some Groups are still at 0% of recovery***

|  |  |  |  |
| --- | --- | --- | --- |
| **Sub county**  | **Group Name**  | **Recovery** | **Remark** |
| Bbaale  | Zibula Atudde | 0  | Groups has conflicts |
| Kamu Kamu  | 0 | Conflicts in the group |
| Kitimbwa  | Muno mu byona  | 0  | Reluctant |
| Kitimbwa Kangulumira  | Kiddawalime | 300,000 out of 2.5 |  Reluctant  |
| Tusitukile wamu  | 400,000 out of 4.8 | Reluctant |
| Kayunga  | Nakaseeta catering  | 300,000 out of 2.8 | Reluctant |
| Nazigo  | Kinyala Coffee nursery  | 0 | Nursery bed was attached by pests |
| Kisega rice growers | 0 | Yet to harvest  |
| KTC | Namagabi B | 0 out of 2.5 | Reluctant |
| Busaana  | BESO  | 0 out of 5.5  | Project still on going  |
| Akutwala Ekiro  | 400,000 out of 5.5 | Project diversified  |

**Challenges**

1. Delay in the realize of funds the MGLSD
2. Out of the 46 groups submitted in phase 2 only 7 were funded.

Kawongo Tompita Kulitalaba Maize grinding mill 6,000,000/=

Kabaku milk traders and value addition milk traders 5,000,000/=

Bwesigwa Developmen group Agro produce 5,040,000/=

 Kayunga Central Cosmetic trade Cosmetics selling 5,000,000/=

Nalumuli poultry Women project Poultry 5,000,000/=

 Bukamba town hair dressing group Hair Dressing 3,000,000/=

Kiwalasi women Soft Drinks group Soft drinks selling 4,800,000/=

 **Total 33,444,000/=**

1. Kinyala Coffee was attached by the pest
2. No marketing for art and Crafts projects

 ***Issues noted***

* Diversification of projects is a good practice by groups
* Many members in the group leading to conflict.
* We recommend for reduction of members to atleast 5
* Women groups have requested for individual loans as opposed to group loans in UWEP.

Namisi Faridah

**Senior Community Development Officer**